## Start Here
Sheets | Purpose
Instructions | Learn about how the PBC-DIDM Data Mapping Tool is used.
Data Mapping Tool | Use this Data Mapping Tool template to record information about the sources of effort and effect being collected in your program.
Action Plan | Use this Action Plan to record actions your Team would like to take related to sources of effort and effect data you are currently collecting or would like to collect in the future.
Schedule | Use this schedule to plan for when, how, and by whom the data will be collected. The sources of effort and effect on this sheet are automatically populated based on the contents entered on the Data Mapping Tool.
Data Mapping Tool - Example | See an example of a PBC-DIDM Data Mapping Tool that was filled out by a program implementing PBC.
Action Plan - Example | See an example of an Action Plan that was filled out by a program. These goals are related to the PBC-DIDM Data Mapping Tool and the sources of effort and effect the program currently collects or wants to collect in the future.
Schedule - Example | See an example of the data collection schedule for one program implementing PBC-DIDM. The sources of effort and effect on this sheet are automatically populated based on the contents entered on the Data Mapping Tool.
Organize your data! | Create a shared PBC-DIDM folder. Within the PBC-DIDM folder create a folder for Data Mapping Tools. Save a copy of this file each time your team edits the contents. Change the date so you always know which file is most current. A recommended file name is: ProgramID-DMT-mm.dd.yyyy For examle: HelpingHands-DMT-08.15.2024

## Instructions
What is the PBC-DIDM Data Mapping Tool?
The PBC-DIDM Data Mapping Tool is one way Leadership Teams and Coaches can record their current Sources of Effort and Effect Data, including key information about who is responsible for collecting, preparing, and sharing the data with others. When measure revisions are identified, or additional sources of data are needed Leadership Teams and Coaches might use the PBC-DIDM Data Mapping Tool to facilitate important conversations about when and how new sources of information will be used. The PBC-DIDM Data Mapping Tool also includes a data collection schedule to help Teams think about and plan for when they will collect each source of effort and effect data. This tool is typically reviewed in detail once a year by the Leadership Team. Then, the Lead Coach or designated member of the Team reviews the Dara Mapping Tool prior to each Leadership Team Meeting to address specific needs.
Click here to learn more about identifying Sources of Effort and Effect Data on the website: pbcdidm.com
How does the PBC-DIDM Data Mapping Tool support other parts of the PBC-DIDM Model?
The PBC-DIDM Data Mapping Tool is aligned with the roles in the PBC-DIDM Implementation Profile (i.e., Leadership, Coaches, and Practitioners). Within each tier of the Profile (i.e., Foundational, Initial, Mid, and Advanced) the indicators contain recommended sources of effort and effect data and processes for when and how these data sources might be collected and reviewed. The PBC-DIDM Data Mapping tool is one way to organize information about which sources of effort and effect data the program already collects and what additional sources of data might be needed.
Click here to learn more about the Implementation Profile on the website: pbcdidm.com
The PBC-DIDM Data Mapping Tool is aligned with the levels of the PBC-DIDM Effort and Effect Cascade (i.e., Leadership, Coaches, Practitioners, and Families). Each of the Cascade levels has an effect on outcomes at another level (e.g., the effects of Coach efforts on Practitioners’ use of practices or Practitioner efforts on child outcomes in a classroom setting). The Cascade supports Leadership Teams, Coaches, and other key stakeholders to identify how effort and effect data are connected and the PBC-DIDM Data Mapping Tool can be used to record the sources of effort and effect data, including when, how, and by whom the data will be collected and prepared.
Click here to learn more about the Effort and Effect Cascade on the website: pbcdidm.com
The PBC-DIDM Data Mapping Tool is aligned with the Prepare part of the Prepare-Look-Think-Act (PLTA) Process which guides Leadership Teams, Coaches, and other key stakeholders to use effort and effect data and other sources of information to make data-informed decisions. One way the Teams or Coaches might Act after engaging in the PLTA Process is to identify revisions to existing sources of effort and effect data or the identification of new measures of effort and effect. The Data Mapping Tool is one way to record revisions or to plan for when, how, and by whom new sources of data will be collected.
Click here to learn more about the Prepare-Look-Think-Act Process on the website: pbcdidm.com
How Use the PBC-DIDM Data Mapping Tool
The steps below are aligned with the PLTA Process for data-informed decision making. Use these steps and the Example tabs to guide your program in using the PBC-DIDM Data Mapping Tool. | Let's get started!
Step 1 Prepare a list of the current measure used to collect data within your program. Then identify where to record them on the "Data Mapping Tool" tab by considering which header listed below is most aligned with the data source. PBC-DIDM Data Mapping Tool Headers: • Program Leadership & Lead PBC Coach Efforts to Support Coaches • Coach Efforts to Support Practitioners (Effect of Leadership/Lead PBC Coach Efforts) • Practitioner Efforts to Support Children & Families (Effect of PBC Coach Efforts) • Child & Family Outcomes (Effect of Coach Efforts)
Click Here to see a Data Mapping Tool Example with mock information from another program.
Click here to begin filling out the Data Mapping Tool for your program.
Step 2 Look at, Think about, and discuss the prompts in each column of the "Data Mapping Tool" tab to clarify and verify current processes for when, how, and by whom current sources of effort and effect data are collected and prepared.
Step 3 Look at, Think about, and discuss the indicators on the PBC-DIDM Implementation Profile aligned to the program's current tier (i.e., Foundational, Initial, Mid, Advanced) and PBC-DIDM implementation goals. Identify if there are recommended sources of effort and effect data or processes not currently in place within the program. Discuss possible Actions the Team might want to take. For example, if the Team rates indicator "FL4. A systematic way to collect quantitative information about Coaches’ use of the PBC framework and essential strategies (e.g., PBC log or checklist)" as 0 - Not yet in place. They might take action by adopting or developing a PBC Log or Checklist for coaches to document their coaching efforts. The Team could us this PBC-DIDM Data Mapping Tool to think about when and how this new source of information would be collected, summarized, and analyzed.
Click here to learn more about the PBC-DIDM Implementation Profile on the website: pbcdidm.com
Step 4 Decide on the Actions the team will take to maintain or enhance the current effort and effect data sources that are being collected. Record these decisions and planned actions in shared location where the actions can be reviewed by the team in the future. Teams might choose to record this information on the "Action Plan" tab in this PBC-DIDM Data Mapping Tool.
Click here to see an Action Plan Example with mock information from another program
Click here to begin filling out the Action Plan for your program.
Use the "Schedule" tab or another program developed too to support the team to communicate the plan for collecting effort and effect data. The schedule can help the Team confirm their plan is feasible given their available resources and commitments. Information from the "Data Mapping Tool" tab is automatically populated in columns A to E of the "Schedule" tab.
Click here to see a Schedule Example with mock information from another program
Click here to begin filling out the Schedule for your program.
Organize your data! Name a copy of this file: ProgramID-DMT-mm.dd.yyyy PBC-DIDM Data Mapping Tool (Version 2.0). Produced by the “Practice-based Coaching Data-Informed Decision Making” model demonstration project funded by the Office of Special Education Programs (#H326M200021, Project Officer: Anita Vermeer). Contents do not necessarily represent the policy of the Department of Education, and you should not assume endorsement by the Federal Government.
For use under Creative Commons license: BY-NC-ND.
For more information, contact pbcdidm@coe.ufl.edu

## Data Mapping Tool
Name of Measure | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes
Program Leadership & Lead PBC Coach Efforts to Support Coaches | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes
Coach Efforts to Support Practitioners (Effect of Leadership/Lead PBC Coach Efforts) | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes
Practitioner Efforts to Support Children & Families (Effect of PBC Coach Efforts) | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes
Child & Family Outcomes (Effect of Coach Efforts) | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes

## Action Plan
Practice-Based Coaching Data-Informed Decision-Making - Data Mapping Tool Action Plan
Site: | Profile Tier at Development:
Date Developed: | Present for Meeting:
Review Date 1: | Present for Meeting:
Review Date 2: | Present for Meeting:
Review Date 3: | Present for Meeting:
Current Activities | Planned activities: Quarter XX (between mm/dd/yy and mm/dd/yy) | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)
Program Leadership & Lead PBC Coach Efforts to Support Coaches | Planned activities: Quarter XX (between mm/dd/yy and mm/dd/yy) | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)
Coach Efforts to Support Practitioners (Effect of Leadership/Lead PBC Coach Efforts) | Planned activities: Quarter XX (between mm/dd/yy and mm/dd/yy) | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)
Practitioner Efforts to Support Children & Families (Effect of PBC Coach Efforts) | Planned activities: Quarter XX (between mm/dd/yy and mm/dd/yy) | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)
Child & Family Outcomes (Effect of Coach Efforts) | Planned activities: Quarter XX (between mm/dd/yy and mm/dd/yy) | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)

## Schedule
Name of Measure Columns A-E are automatically populated from the Data Mapping Tool | How often will the data be collected? | Notes | Who will collect the data? | Notes | [12 empty] | Were the data collected as planned? | Were the data collected as planned? | Were the data collected as planned? | Were the data collected as planned? | Notes
Program Leadership & Lead PBC Coach Efforts to Support Coaches | How often will the data be collected? | Notes | Who will collect the data? | Notes | July | August | September | October | November | December | January | February | March | April | May | June | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Updated: mm.dd.yyyy
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
Coach Efforts to Support Practitioners (Effect of Leadership/Lead PBC Coach Efforts) | How often will the data be collected? | Notes | Who will collect the data? | Notes | July | August | September | October | November | December | January | February | March | April | May | June | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Updated: mm.dd.yyyy
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
Practitioner Efforts to Support Children & Families (Effect of PBC Coach Efforts) | How often will the data be collected? | Notes | Who will collect the data? | Notes | July | August | September | October | November | December | January | February | March | April | May | June | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Updated: mm.dd.yyyy
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
Child & Family Outcomes (Effect of Coach Efforts) | How often will the data be collected? | Notes | Who will collect the data? | Notes | July | August | September | October | November | December | January | February | March | April | May | June | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Updated: mm.dd.yyyy
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0

## Data Mapping Tool-Example
Name of Measure | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes
Program Leadership & Lead PBC Coach Efforts to Support Coaches | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes
PBC Workshop Attendance | Attendance | Active | Lead Coaches |  | Other (describe in notes) | Paper and then excel sheet | Following event |  | Other (describe in notes) | Following event | Lead Coaches |  | Leadership Team |  | Lead Coaches |  | Yes | Yes | Number of coaches trained
PBC Workshop Implementation Checklist | Professional Learning Implementation | Active | Lead Coaches |  | Paper | Save to drive | Following event |  | Other (describe in notes) | Following event to identify if make-up content needs to be addressed in Coach Community Meetings or booster Professional Learning Experiences | Lead Coaches |  | Leadership Team |  | Lead Coaches |  | No | No
PBC Workshop Participant Evaluation | Social Validity or Feedback | Active | Lead Coaches |  | Electronic Forms |  | Following event |  | Other (describe in notes) | Following event | Lead Coaches |  | Leadership Team |  | Lead Coaches |  | No | No
Coach Community Meeting Attendance | Attendance | Active | Lead Coaches |  | Other (describe in notes) | Paper and then excel sheet | Monthly |  | Quarterly | Review with coach during quarterly review | Lead Coaches |  | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | No | No
Coach Community Meeting Log | Professional Learning Implementation | Active | Lead Coaches |  | Electronic Forms |  | Monthly |  | Quarterly |  | Lead Coaches | With Data Manager Support | Leadership Team |  | Lead Coaches |  | No | No
Coach Community Meeting Participant Evaluation | Social Validity or Feedback | Active - Revision Needed | Lead Coaches |  | Electronic Forms |  | Monthly |  | Other (describe in notes) | Following event | Lead Coaches |  | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | No | No
PBC Implementation Check Log | PBC Implementation | Development in Progress | Lead Coaches |  | Electronic Forms | Paper available if needed prior to entry | Other (describe in notes) | Quarterly | Quarterly | To identify individual Coach supports and Coach Community Meeting topics | Lead Coaches | With Data Manager Support | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | Yes | Yes | Quality of support provided by Coaches
Leadership Team and Coach Feedback Survey | Social Validity or Feedback | Active - Revision Needed | Lead Coaches |  | Electronic Forms |  | Twice | Fall and Spring | Other (describe in notes) | Twice a year - Fall and Spring | Other (describe in notes) | Data Manager | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | No | No
Coach Efforts to Support Practitioners (Effect of Leadership/Lead PBC Coach Efforts) | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes
Practitioner Partnership Agreement | Other | Active - Revision Needed | Coaches |  | Other (describe in notes) | PDF to drive | Once | At the beginning of the PBC Cycle | Quarterly | Quarterly report - count of practitioners served | Lead Coaches |  | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | Yes | Yes | Number of practitioners served
Action Plan | PBC Implementation | Active | Coaches |  | Other (describe in notes) | Paper scan to drive | Other (describe in notes) | As needed throughout PBC | Other (describe in notes) | As needed to support individual Coaches | Lead Coaches |  | Coach |  | Lead Coaches |  | No | No
PBC Log | PBC Implementation | Active | Coaches |  | Electronic Forms | Paper available if needed prior to entry | Weekly | Following each weekly PBC session | Quarterly | Quarterly report and implementation check meeting with each coach for their quarterly review | Lead Coaches | With Data Manager Support | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | Yes | Yes | Quantity, quality, and content focus of PBC services
Practitioner Feedback Survey | Social Validity or Feedback | Active - Revision Needed | Coaches |  | Electronic Forms | Paper available if needed prior to entry | Once | At the end of the PBC Cycle | Quarterly | Quarterly to shared in Coach Community Meeting and in quarterly report | Lead Coaches |  | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | Yes | Yes | Practitioner satisfaction
T/A not PBC Form | Other | Need to Develop | Coaches |  | Electronic Forms |  | Following event | When TA that is not PBC is provided | Quarterly | Quarterly to shared in Coach Community Meeting and in quarterly report | Lead Coaches | With Data Manager Support | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | Yes | Yes | Quantity and focus of other TA
Practitioner Efforts to Support Children & Families (Effect of PBC Coach Efforts) | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes
Practitioner All About Me Form | Demographics | Active | Coaches | Completed by practitioner and collected by coach | Electronic Forms | Paper available if needed prior to entry | Once | At the beginning of the PBC Cycle | Quarterly | Gather information about practitioner experience prior to PBC | Other (describe in notes) | Data Manager | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | Yes | Yes | Practitioner Demographics
Practitioner Strengths and Needs | Practitioner Practice Implementation | Active | Coaches | Completed by practitioner and collected by coach | Electronic Forms | Paper available if needed prior to entry | Three times | Beginning, Middle, and End of PBC Cycle | Quarterly | Identify self-reported growth for practitioners who have completed the PBC Cycle | Other (describe in notes) | Data Manager | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | Yes | Yes | Practitioner self-reported progress
Anita Zucker Center Foundational Effective Practices Observation Checklist | Practitioner Practice Implementation | Active | Coaches |  | Electronic Forms | Paper available if needed prior to entry | Three times | Beginning, Middle, and End of PBC Cycle | Quarterly | Identify observed growth for practitioners who have completed the PBC Cycle | Other (describe in notes) | Data Manager | Multiple (describe in notes) | Leadership Team, Lead Coach, and Coaches | Lead Coaches |  | Yes | Yes | Practitioner observed progress
Child & Family Outcomes (Effect of Coach Efforts) | PBC-DIDM Type of Data | Status | Who will collect the data? | Notes | How will the data be collected? | Notes | How often will the data be collected? | Notes | How often will the data be prepared for review? | Notes | Who will verify the data are complete and prepare the data summary? | Notes | Who will receive the prepared data? | Notes | Who will teach others to collect and enter the data? | Notes | Part of Quarterly Report | Part of Annual Report | Notes
Assessment of Student Thinking - Start Early Literacy | Child(Family) Progress | Active | Practitioners |  | State System |  | Twice | Fall and Spring | Other (describe in notes) | Fall and Spring | Other (describe in notes) | Data Manager | Multiple (describe in notes) | Leadership Team, Lead Coach, Coaches, Practitioners, and Families | Other (describe in notes) | External consultant | Yes | Yes | Child progress
Number of IEP goals met | Child(Family) Progress | Active | Practitioners |  | State System |  | Annual |  | Annual |  | Other (describe in notes) | Data Manager | Multiple (describe in notes) | Leadership Team, Lead Coach, Coaches, Practitioners, and Families | Other (describe in notes) | External consultant | Yes | Yes | Child progress
Annual Family Survey | Social Validity or Feedback | Active | Leadership |  | Electronic Forms | Paper available if needed prior to entry | Annual | Spring | Annual | Annual report | Other (describe in notes) | Data Manager | Multiple (describe in notes) | Leadership Team, Lead Coach, Coaches, Practitioners, and Families | Lead Coaches |  | Yes | Yes | Family satisfaction and self-efficacy

## Action Plan - Example
Practice-Based Coaching Data-Informed Decision-Making - Data Mapping Tool Action Plan
Site: Example | Profile Tier at Development: Initial
Developed: August 15 | Present: Jaynesha, Hailey, Rena, Mike (Samantha out on leave)
Review 1: October 17 | Present: Jaynesha, Hailey, Rena, Mike, Samantha
Review 2: | Present:
Review 3: | Present:
Current Activities | Planned activities: Quarter 2 (between 10/1 and 1/1 | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)
Program Leadership & Lead PBC Coach Efforts to Support Coaches | Planned activities: Quarter 2 (between 10/1 and 1/1 | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)
Coach Community Meeting Participant Evaluation currently collected monthly with a focus on content. | Revise form to add space for open-text responses and a place to check off preferred facilitation or engagement strategies. Send Revisions out by 10/1 Review revisions on 10/15 Begin using 11/1 | Lead Coach (Jaynesha/Hailley) | 2024-11-01 | 10/17 - Revisions approved
PBC Implementation Check Log - Currently Lead Coach reviews videos and provides written feedback, but a formal log and process are not in place. | Develop a Log that can guide the PBC Implementation Check process for current and new Lead PBC Coaches. Align indicators to observe with the PBC Log. Review form on 10/15 and edit as needed with the Leadership Team Have this in place for the third quarter | Lead Coach (Jaynesha/Hailley) | 2024-01-01 | 10/17 - Lead Coach (Jaynesha) pilot with 2-3 videos to see how it might work and set up electronic form with Data Manager (Len) for review during December meeting
Leadership Team and Coach Feedback Survey currently collected fall and spring. | Revise form to add a branching logic for coaches to answer additional questions related to their individual supports received through the quarterly implementation check and formal review process. Send Revisions out by 10/1 Review revisions on 10/15 Begin using 11/1 | Lead Coach (Jaynesha/Hailley) | 2024-11-01 | 10/17 - Revisions approved
Coach Efforts to Support Practitioners (Effect of Leadership/Lead PBC Coach Efforts) | Planned activities: Quarter 2 (between 10/1 and 1/1 | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)
Practitioner Partnership Agreement - Currently signed on paper at the beginning of the PBC Cycle. | Revise to add a space for the Practitioners name in print, work email, and phone number No review needed by Leadership Team | Lead Coach (Jaynesha/Hailley) | 2024-10-01 | 10/17 - These edits were made and the new form will be in use as of 10/20. Delay in update due to sharing the new form on the Coach Community Meeting call and ensuring Coaches had access to printed copies. Update tag on Data Mapping Tool to "Active"
Practitioner Feedback Survey - Captures feedback about what occurred with the Coach. | Revise and add items related to sustainability supports and how Practitioners might want to continue to engage with the Coach or colleagues in a group format once individual PBC has ended. Bring draft items to the December Leadership Team meeting, Invite Hailey to joining for that part of the agenda. | Lead Coach (Jaynesha/Hailley) | 2024-01-15 | 10/17 - Len has been assigned to support with this revision
T/A not PBC Form - We're not currently recording support that occurs outside of PBC, but Coaches often provide support between meetings to drop off resources or to observe specific children. | Work with Coach Community to identify the categories of support that should be included on the form. Bring draft items to the November Leadership Team meeting, Invite Hailey to joining for that part of the agenda. | Lead Coach (Jaynesha/Hailley) | 2024-01-15 | 10/17 - We have this on the agenda for the October Coach Community Meeting
Practitioner Efforts to Support Children & Families (Effect of PBC Coach Efforts) | Planned activities: Quarter 2 (between 10/1 and 1/1 | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)
Child & Family Outcomes (Effect of Coach Efforts) | Planned activities: Quarter 2 (between 10/1 and 1/1 | Who is leading this effort? | Date of planned completion | What progress have we made? (Note date discussed and provide update)

## Schedule - Example
Name of Measure Columns A-E are automatically populated from the Data Mapping Tool | How often will the data be collected? | Notes | Who will collect the data? | Notes | [12 empty] | Were the data collected as planned? | Were the data collected as planned? | Were the data collected as planned? | Were the data collected as planned? | Notes
Program Leadership & Lead PBC Coach Efforts to Support Coaches |  | Notes | Who will collect the data? | Notes | July | August | September | October | November | December | January | February | March | April | May | June | Review Date: 11.01.2024 | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Updated: 11.01.2024
PBC Workshop Attendance | Following event |  | Lead Coaches | Hailey |  | X | [10 empty] | Yes = 100% collected
PBC Workshop Implementation Checklist | Following event |  | Lead Coaches | Hailey |  | X | [10 empty] | Yes = 100% collected
PBC Workshop Participant Evaluation | Following event |  | Lead Coaches | Hailey |  | X | [10 empty] | Yes = 100% collected
Coach Community Meeting Attendance | Monthly |  | Lead Coaches | Jaynesha |  | Ongoing | [10 empty] | Yes = 100% collected
Coach Community Meeting Log | Monthly |  | Lead Coaches | Jaynesha |  | Ongoing | [10 empty] | Yes = 100% collected
Coach Community Meeting Participant Evaluation | Monthly |  | Lead Coaches | Jaynesha |  | Ongoing | [10 empty] | Yes = 100% collected
PBC Implementation Check Log | Other (describe in notes) | Quarterly | Lead Coaches | Hailey/Jaynesha | X - Summer Program ONLY |  |  | X |  |  | X |  |  | X |  |  | Use PLTA Process to decide on actions |  |  |  | Technology was an issue this summer, but we've been successful with the October checks. No additional actions needed.
Leadership Team and Coach Feedback Survey | Twice | Fall and Spring | Lead Coaches | Jaynesha |  |  | X |  |  |  |  | X |  |  |  |  | Yes = 100% collected
Coach Efforts to Support Practitioners (Effect of Leadership/Lead PBC Coach Efforts) |  | Notes | Who will collect the data? | Notes | July | August | September | October | November | December | January | February | March | April | May | June | Review Date: 11.01.2024 | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Updated: 11.01.2024
Practitioner Partnership Agreement | Once | At the beginning of the PBC Cycle | Coaches | Each Coach |  |  |  | X |  |  | X |  |  | X - Summer Program ONLY |  |  | Yes = 100% collected
Action Plan | Other (describe in notes) | As needed throughout PBC | Coaches | Each Coach | X - Summer Program ONLY |  |  | Ongoing | [8 empty] | Yes = 100% collected
PBC Log | Weekly | Following each weekly PBC session | Coaches | Each Coach | X - Summer Program ONLY |  |  | Ongoing | [8 empty] | Yes = 100% collected
Practitioner Feedback Survey | Once | At the end of the PBC Cycle | Coaches | Jaynesha creates link and coaches prompt | X - Summer Program ONLY |  |  |  |  | X |  |  | X |  |  |  | NA
T/A not PBC Form | Following event | When TA that is not PBC is provided | Coaches | Each Coach | X - Summer Program ONLY |  |  | Ongoing | [8 empty] | Use PLTA Process to decide on actions |  |  |  | Coaches have had some questions about what counts as TA (i.e., only site visits or email and phone support). Plan for Coach Community Meeting to support with guidance.
Practitioner Efforts to Support Children & Families (Effect of PBC Coach Efforts) |  | Notes | Who will collect the data? | Notes | July | August | September | October | November | December | January | February | March | April | May | June | Review Date: 11.01.2024 | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Updated: 11.01.2024
Practitioner All About Me Form | Once | At the beginning of the PBC Cycle | Coaches | Completed by practitioner and collected by coach |  |  |  | X |  |  | X |  |  | X - Summer Program ONLY |  |  | Yes = 100% collected
Practitioner Strengths and Needs | Three times | Beginning, Middle, and End of PBC Cycle | Coaches | Completed by practitioner and collected by coach | X - Summer Program ONLY |  |  | Ongoing | [8 empty] | Partial = 75% or more collected |  |  |  | We need to ensure coaches have printed copies handy just in case the practitioner doesn't complete the electronic form. Could the Diector keep a binder on site for the Coach? Coaches could have a "go bag" - talk with coaches.
Anita Zucker Center Foundational Effective Practices Observation Checklist | Three times | Beginning, Middle, and End of PBC Cycle | Coaches | Each Coach |  |  | X |  |  |  | X |  |  | X |  |  | Yes = 100% collected
Child & Family Outcomes (Effect of Coach Efforts) |  | Notes | Who will collect the data? | Notes | July | August | September | October | November | December | January | February | March | April | May | June | Review Date: 11.01.2024 | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Review Date: mm.dd.yyyy | Updated: 11.01.2024
Assessment of Student Thinking - Start Early Literacy | Twice | Fall and Spring | Practitioners | Each Practitioner with Len's Support |  |  | X |  |  |  |  | X
Number of IEP goals met | Annual |  | Practitioners | Each Practitioner with Len's Support | [5 empty] | X |  |  |  |  | X
Annual Family Survey | Annual | Spring | Leadership | Hannah/Linda | [7 empty] | X